## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Ticket submission interface for capturing issue descriptions from users | MUST HAVE | None | Backend | 3- Completed
Sprint 1 | Sprint 1 | US-02 | Text preprocessing and normalization of ticket descriptions for ML input | MUST HAVE | US-01 | ML | 3- Completed
Sprint 1 | Sprint 1 | US-03 | Automated ticket category classification using trained machine learning model | MUST HAVE | US-02 | ML | 3- Completed
Sprint 1 | Sprint 1 | US-04 | Automated ticket priority prediction using machine learning | MUST HAVE | US-02 | ML | 3- Completed
Sprint 1 | Sprint 1 | US-05 | Persistent ticket storage using SQLite database | MUST HAVE | US-03, US-04 | Backend | 3- Completed
Sprint 2 | Sprint 2 | US-06 | Entity extraction from ticket text (users, devices, error codes) | MUST HAVE | US-02 | ML | 3- Completed
Sprint 2 | Sprint 2 | US-07 | Rule-based priority escalation for critical incidents | MUST HAVE | US-04 | ML | 3- Completed
Sprint 2 | Sprint 2 | US-08 | Ticket listing and management interface for support team | MUST HAVE | US-05 | Frontend | 3- Completed
Sprint 2 | Sprint 2 | US-09 | Ticket status update workflow (Open, In-Progress, Resolved, Closed) | MUST HAVE | US-08 | Frontend | 3- Completed
Sprint 2 | Sprint 2 | US-10 | SLA calculation and visual indication based on ticket age | SHOULD HAVE | US-05 | Frontend | 3- Completed
Sprint 3 | Sprint 3 | US-11 | Role-based authentication and access control | MUST HAVE | US-05 | Backend | 3- Completed
Sprint 3 | Sprint 3 | US-12 | Role-specific user interface rendering | MUST HAVE | US-11 | Frontend | 3- Completed
Sprint 3 | Sprint 3 | US-13 | Dashboard with ticket metrics and analytics | MUST HAVE | US-05 | Frontend | 3- Completed
Sprint 3 | Sprint 3 | US-14 | Notification generation for high-priority tickets | SHOULD HAVE | US-04 | Backend | 3- Completed
Sprint 4 | Sprint 4 | US-15 | Machine-learning-based Named Entity Recognition using spaCy | COULD HAVE | US-06 | ML | 3- Completed
Sprint 4 | Sprint 4 | US-16 | Regex-based fallback entity extraction mechanism | MUST HAVE | US-15 | ML | 3- Completed
Sprint 4 | Sprint 4 | US-17 | Ticket filtering by status and priority | SHOULD HAVE | US-08 | Frontend | 3- Completed
Sprint 4 | Sprint 4 | US-18 | Automatic interface refresh for real-time ticket updates | COULD HAVE | US-08 | Frontend | 3- Completed
Sprint 4 | Sprint 4 | US-19 | Archived view for closed tickets | COULD HAVE | US-09 | Frontend | 3- Completed
Sprint 4 | Sprint 4 | US-20 | Display of ML confidence scores for category and priority predictions | COULD HAVE | US-03 | ML | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID |  | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
| Task ID | [6 empty] | 54 | 4 | 2 | 6 | 6 | 7 | 11 | 7 | 4 | 5 | 2 | 0 | 0 | 0 | 0
US-01 | T-01 | Design ticket input workflow and API contract | 2025-12-02 | 2025-12-02 | Neha Miriam Jose | Design | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Implement FastAPI endpoint for ticket submission | 2025-12-02 | 2025-12-03 | Neha Miriam Jose | Coding | Completed | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-03 | Implement text preprocessing logic | 2025-12-03 | 2025-12-04 | Neha Miriam Jose | Coding | Completed | 5 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-04 | Train ML model for ticket category classification | 2025-12-04 | 2025-12-06 | Neha Miriam Jose | Build | Completed | 10 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-05 | Train ML model for priority prediction | 2025-12-05 | 2025-12-07 | Neha Miriam Jose | Design | Completed | 8 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-06 | Design SQLite database schema for tickets | 2025-12-06 | 2025-12-06 | Neha Miriam Jose | Coding | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-07 | Implement ticket persistence logic in database | 2025-12-06 | 2025-12-07 | Neha Miriam Jose | Integreation test | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-08 | Integrate ML predictions with database insertion | 2025-12-07 | 2025-12-08 | Neha Miriam Jose | Integeration test | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-09 | Validate user input and error handling | 2025-12-08 | 2025-12-09 | Neha Miriam Jose | Unit test | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-03 | T-10 | End-to-end testing of ticket generation flow | 2025-12-09 | 2025-12-10 | Neha Miriam Jose | System test | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Unclear dataset labels for category classification | Reviewed dataset and standardized category labels
Sprint 1 | Day 4 | ML model accuracy was initially low | Tuned TF-IDF parameters and retrained model
Sprint 1 | Day 6 | Database schema mismatch during insertion | Updated SQLite schema and aligned insert queries
Sprint 1 | Day 8 | API returned errors for empty input | Added input validation and error handling
Sprint 1 | Day 10 | End-to-end flow failing intermittently | Debugged integration points and fixed API–ML binding
Sprint 2 | Day 1 | Difficulty identifying entities using regex only | Designed spaCy-based NER approach
Sprint 2 | Day 3 | spaCy model not loading in some environments | Added fallback regex-based entity extraction
Sprint 2 | Day 5 | Priority escalation rules were inconsistent | Refined rule-based logic for critical keywords
Sprint 2 | Day 7 | UI table not refreshing after status update | Implemented rerun logic in Streamlit
Sprint 2 | Day 9 | SLA calculation showing incorrect hours | Corrected time difference calculation logic
Sprint 3 | Day 2 | User roles not persisting after refresh | Stored role data in session state
Sprint 3 | Day 4 | Dashboard metrics not updating dynamically | Refactored data fetch logic
Sprint 3 | Day 6 | High-priority notifications not triggering | Fixed priority condition check
Sprint 3 | Day 8 | Filters not combining status and priority correctly | Corrected filter logic sequence
Sprint 3 | Day 10 | Performance lag with larger ticket volume | Optimized database queries
Sprint 3 | Day 2 | User roles not persisting after refresh | Stored role data in session state
Sprint 3 | Day 4 | Dashboard metrics not updating dynamically | Refactored data fetch logic
Sprint 3 | Day 6 | High-priority notifications not triggering | Fixed priority condition check
Sprint 3 | Day 8 | Filters not combining status and priority correctly | Corrected filter logic sequence
Sprint 3 | Day 10 | Performance lag with larger ticket volume | Optimized database queries

## Retrospection
SL # | SL # | SL # | SL # | SL # | SL # | SL # | SL # | SL #
1 | Sprint 1 | Ticket creation and ML integration completed | Initial ML accuracy was low | Dataset preprocessing issues | TF-IDF tuning and retraining | Learned ML pipeline integration | Good coordination | Sprint goal achieved
2 | Sprint 2 | Entity extraction and hybrid logic implemente | spaCy dependency issues | External library handling | Regex fallback added | Importance of fail-safe design | Effective collaboration | Sprint completed successfully
3 | Sprint 3 | Role-based login and dashboard completed | Session state issues | UI state management | Session handling improved | Role-based UI control | Team communication improved | Features stabilized
4 | Sprint 4 | Testing and documentation completed | Minor UI validation issues | Final alignment of docs | Regression testing done | Importance of final testing | Strong coordination | Project completed