## Sheet1
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Action Taken | Type of Defect | Action Taken Date | Status(Open/Closed)
1 | Neha Miriam Jose | 2025-12-04 | Ticket submission allowed empty description | Sprint 1 | Neha Miriam Jose | Added input validation and error handling | Function | 2025-12-05 | Closed
2 | Neha Miriam Jose | 2025-12-06 | Incorrect category predicted for similar tickets | Sprint 1 | Neha Miriam Jose | Improved preprocessing and retrained ML model | Logical | 2025-12-07 | Closed
3 | Neha Miriam Jose | 2025-12-08 | Ticket data not stored due to schema mismatch | Sprint 1 | Neha Miriam Jose | Updated SQLite schema and insert query | Data | 2025-12-08 | Closed
4 | Neha Miriam Jose | 2025-12-17 | Entity extraction failed when spaCy model unavailable | Sprint 2 | Neha Miriam Jose | Implemented regex-based fallback mechanism | Configuration | 2025-12-18 | Closed
5 | Neha Miriam Jose | 2025-12-20 | High-priority tickets not visually highlighted | Sprint 2 | Neha Miriam Jose | Corrected priority condition logic | Functional | 2025-12-21 | Closed
6 | Neha Miriam Jose | 2026-01-02 | User role lost after page refresh | Sprint 3 | Neha Miriam Jose | Stored role in session state | UI | 2026-01-03 | Closed
7 | Neha Miriam Jose | 2026-01-05 | Dashboard metrics not refreshing automatically | Sprint 3 | Neha Miriam Jose | Refactored data fetch logic | Functional | 2026-01-06 | Closed
8 | Neha Miriam Jose | 2026-01-14 | Excel effort entry blocked by validation limits | Sprint 4 | Neha Miriam Jose | Updated data validation limits | Usability | 2026-01-14 | Closed
9 | Neha Miriam Jose | 2026-01-16 | Ticket table alignment inconsistent across screens | Sprint 4 | Neha Miriam Jose | Adjusted layout and styling | UI | 2026-01-17 | Closed
10 | Neha Miriam Jose | 2026-01-19 | Code comments and documentation not standardized | Sprint 4 | Neha Miriam Jose | Updated final documentation | Documentation | 2026-01-20 | Closed